## backlog
PROJECT BACKLOG v1.0
				TIME	VALUE
Look at other projects mechanizing metatheory				5	6
Look at other projects on logical relations				5	5
Look at projects on compiler correctness				5	3
Look at Amal Ahmed's work				5	4
Look at project CONCERT				5	5
Do POPLmark				25	7
Look at the mechanized metatheory challenge				1	6
Finish first draft of paper minus introduction and conclusion				14.25	10
First draft of introduction and conclusion				5	10
Second draft of paper				5	9
Final draft of paper				5	8
Finish formalization				50	9
TOTAL				130.25

CAPACITY	3	per day
DATE OF COMPLETION		08/09/16

VERSION 0.1		START	28/06/16	END	02/07/16	ETA v1.0	05/09/16	CAPACITY	3
SPRINT GOAL		Finish the first draft of the paper minus introduction and conclusion
Finish first draft of paper minus introduction and conclusion				14.25	10